SOVEREIGN ARMS FOUNDATION UGANDA (SAFU)
Annual Work Plan & Budget (2025–2026)

1. Overview

This one-year work plan and budget outlines the core activities, objectives, and estimated costs for Sovereign Arms Foundation Uganda (SAFU) for the period July 2025 – June 2026. The plan is designed to support our mission of building sovereignty through service, focusing on youth empowerment, digital literacy, leadership development, and peacebuilding.

2. Work Plan Summary

| Quarter | Key Activities | Objectives | Target Area | Responsible Department |
| --- | --- | --- | --- | --- |
| Q1 (Jul – Sep 2025) | Launch & Community Mobilization | Introduce SAFU to communities, register members | Central Uganda (Pilot) | Executive & Publicity |
|  | Leadership & Civic Training Camp | Train 50 youth leaders | Kampala | Programs |
|  | Digital Literacy Bootcamp | ICT training for 40 youth | Mukono | Programs |
| Q2 (Oct – Dec 2025) | Peacebuilding & Security Forums | Engage local leaders/youth on community peace | Jinja | Programs |
|  | Community Clean-Up Campaign | Promote volunteerism | Kampala Slums | Publicity/Programs |
|  | Constitution & Governance Workshop | Strengthen internal governance | Kampala | Secretariat |
| Q3 (Jan – Mar 2026) | Women & Youth Skills Training | Train 50 in entrepreneurship & life skills | Busia | Programs |
|  | School Outreach Program | Civic education in 5 schools | Eastern Uganda | Education Unit |
| Q4 (Apr – Jun 2026) | Annual General Meeting (AGM) | Review progress, elect leaders | Kampala | Secretariat |
|  | NGO Bureau Compliance Audit | Submit reports, file updates | Kampala | Treasurer/Admin |

3. Budget Estimate (UGX)

| Activity | Estimated Cost (UGX) |
| --- | --- |
| Registration & Legal Setup | 1,500,000 |
| Digital Literacy Bootcamps (2 rounds) | 4,000,000 |
| Youth Leadership Camp | 3,500,000 |
| Peace & Security Dialogues (2 forums) | 2,000,000 |
| School Outreach (transport, materials) | 1,200,000 |
| Women/Youth Skills Training | 3,800,000 |
| AGM & Reporting | 2,000,000 |
| Communication & Publicity | 1,000,000 |
| Office Stationery & Printing | 800,000 |
| Transport & Coordination | 2,200,000 |
| Contingency (10%) | 2,000,000 |
| Total Estimate | 24,000,000 |

4. Notes:

The above budget is a projection and will be reviewed quarterly.

SAFU will seek funding from grants, donations, member contributions, and fundraising activities.

Priority will be given to activities that create direct community impact and visibility.

Prepared by: SAFU Secretariat
Date: July 2025